## Project Timeline
EduCore Learning Institute - Staff Scheduling Mobile Application
Project Duration: 10 Months (Estimated)
Expected Start Date: March 2025
Phase | Key Deliverables | Duration | Stakeholder | Weeks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Phase 1: Project Initiation and Planning | Approved project charter | 4 Weeks | bar: Weeks 1 to Weeks 4
Stakeholder engagement plan | bar: Weeks 1 to Weeks 4
Risk assessment | bar: Weeks 1 to Weeks 4
Resource and governance planning | bar: Weeks 1 to Weeks 4
1 Month | bar: Weeks 1 to Weeks 5
Phase 2: Requirements and Design | Software Requirements Specification (SRS) | 10 Weeks | bar: Weeks 5 to Weeks 14
System architecture design | bar: Weeks 5 to Weeks 14
Database design | bar: Weeks 5 to Weeks 14
UI/UX mockups and prototypes | bar: Weeks 5 to Weeks 14
Interface specifications | bar: Weeks 5 to Weeks 14
Phase 3: System Development | Mobile app development (iOS & Android) | 16 Weeks | bar: Weeks 15 to Weeks 30
Backend systems and services | bar: Weeks 15 to Weeks 30
Integrated system components | bar: Weeks 15 to Weeks 30
Phase 4: Testing and Validation | Integration and system testing | 6 Weeks | bar: Weeks 31 to Weeks 36
Performance and security testing | bar: Weeks 31 to Weeks 36
Bug fixes and regression testing | bar: Weeks 31 to Weeks 36
User Acceptance Testing (UAT) and refinement | bar: Weeks 31 to Weeks 36
Phase 5: Deployment and Training | Live production system | 4 Weeks | bar: Weeks 37 to Weeks 40
User training sessions | bar: Weeks 37 to Weeks 40
Documentation and user manuals | bar: Weeks 37 to Weeks 40
Phase 6: Stabilisation and Closure | Post-deployment support and issue resolution | 3 Weeks | bar: Weeks 41 to Weeks 43
Final documentation | bar: Weeks 41 to Weeks 43
Project handover | bar: Weeks 41 to Weeks 43
Key Milestones | bar: Weeks 1
Milestone | Description | Target Date | bar: Weeks 1
M1 | Project Kick-off & Planning Approval | End of Month 1
M2 | SRS & Design Approval | End of Month 3
M3 | Development Complete | End of Month 6
M4 | UAT Approval | End of Month 8
M5 | Go-Live / Production Launch | End of Month 9
M6 | Project Sign-off | End of Month 10
Important Notes for Vendors | bar: Weeks 1 to Weeks 13
1. Timeline: The timeline is indicative and subject to final agreement. Vendors may propose alternative timelines with justification.
2. Deliverables: Each phase must conclude with formal acceptance of deliverables by EduCore before proceeding to the next phase.
3. Payment Terms: Payment milestones will be tied to successful completion and acceptance of phase deliverables.
4. Resources: Vendors must specify resource allocation, team composition, and availability in their proposal.
5. Communication: Weekly progress reports and bi-weekly review meetings are mandatory throughout the project.
6. Changes: Any changes to scope, timeline, or deliverables must be formally documented and approved through change control process.
7. Documentation: All technical documentation, user manuals, and source code must be delivered as part of final handover.
8. Support: Vendors must include post-deployment support plan (minimum 3 months) in their proposal.
Vendor Proposal Requirements | bar: Weeks 1 to Weeks 13
• Company profile and relevant experience in education technology solutions
• Proposed technical approach and methodology
• Detailed project plan with timeline and milestones
• Team composition and CVs of key personnel
• Detailed cost breakdown by phase and deliverable
• Quality assurance and testing approach
• Risk management plan
• Post-implementation support and maintenance plan
• References from similar projects (minimum 2)
• Proposed contract terms and conditions
EduCore Learning Institute Pte Ltd ¦ Confidential Document